## Form Editor
Scenario | Method to Test | Tested | Assignee | Scenario | Method to Test | Tested | Assignee | Scenario | Method to Test | Tested | Assignee
Click on Admin Panel | Automate | Yes | Crystal | Export Form* |  |  |  | Additional Actions (Need to be expanded)
Click on Form Editor | Automate | Yes | Crystal | Open an existing form | Automate | Yes | Crystal | Edit question | Select Method | No | Select Tester
Create a New Form |  |  |  | Click on Export Form | Automate | Yes | Crystal | Make question required | Select Method | No | Select Tester
Click on Create Form | Automate | Yes | Crystal | Select where to save and click Save | Automate | Yes | Crystal | Archive a question | Select Method | No | Select Tester
Enter form name and description | Automate | Yes | Crystal | Import Form* |  |  |  | Delete a question | Select Method | No | Select Tester
Click on Save | Automate | Yes | Crystal | Click on Form Browser link | Automate | Yes | Crystal | Mark a question as PHI/PII | Select Method | No | Select Tester
Verify Form Editor is displayed | Automate | Yes | Crystal | Click on Import Form | Automate | Yes | Crystal | Preview Form | Select Method | No | Select Tester
Add Section to Form |  |  |  | Click on Choose File | Automate | Yes | Crystal | Edit form again | Select Method | No | Select Tester
Click on Add Section | Automate | Yes | Crystal | Select form and click Open | Automate | Yes | Crystal | Link form to Workflow | Select Method | No | Select Tester
Input Section Heading | Automate | Yes | Crystal | Verify Form name is displayed in window | Automate | Yes | Crystal | Test form in New Request | Select Method | No | Select Tester
Click Save | Automate | Yes | Crystal | Click on Import | Automate | Yes | Crystal | Add sort priorty to question | Select Method | No | Select Tester
Verify New Section has been added | Automate | Yes | Crystal | Verify Form name is under the Supplemental Forms section | Automate | Yes | Crystal | Staple other form | Select Method | No | Select Tester
If/Then Using Prefill Conditions* |  |  |  | Add Internal Use Form to Form* |  |  |  | Edit stapled form's properties | Select Method | No | Select Tester
Click on "+ Add Question to Section" | Automate | Yes | Crystal | Select existing form that requires the internal use form | Automate | Yes | Crystal | Confirm stapled form is attached | Select Method | No | Select Tester
Fill in text fields and then click on the Input Format drop down | Automate | Yes | Crystal | Click on "+ Add Internal Form" | Automate | Yes | Crystal | Remove stapled form | Select Method | No | Select Tester
Select Dropdown Menu (single select, multiple options) | Automate | Yes | Crystal | Verify New Internal Use Form window is displayed | Automate | Yes | Crystal
Click Save | Automate | Yes | Crystal | Fill in name and optional description and click Save | Automate | Yes | Crystal | *Priority set by Harlie.
Verify question has been added to the form | Automate | Yes | Crystal | Verify Internal Use Form is Visible*
Click on "+ Sub-Question" | Automate | Yes | Crystal | Go back to the main form by clicking on its title on the left side | Automate | Yes | Crystal
Fill in the field name and select desired Input Format | Automate | Yes | Crystal | Click on View Workflow | Automate | Yes | Crystal
Click Save | Automate | Yes | Crystal | Verify Workflow is displayed | Automate | Yes | Crystal
Verify sub-question has been added | Automate | Yes | Crystal | Click on the step to where you want to add the Internal Form | Automate | Yes | Crystal
Click on Modify Logic | Automate | Yes | Crystal | Under Form Field, select the Internal form that you created | Automate | Yes | Crystal
Click on "+ New Condition" | Automate | Yes | Crystal | Delete Form
Choose "Pre-fill this Question" from the dropdown | Automate | Yes | Crystal | Select the "Delete Form" button | Automate | Yes | Crystal
Provide the expected response in "Enter a pre-fill" value | Automate | Yes | Crystal | Select "Yes" from the pop up | Automate | Yes | Crystal
Set the condition values in the "IF" Row | Automate | Yes | Crystal | Verify the form is no long in the list | Automate | Yes | Crystal
Click Save | Automate | Yes | Crystal
Verify the condition is displayed on the new Window | Automate | Yes | Crystal
Add more conditions if desired then click Close | Automate | Yes | Crystal
Note on F2: Kirscht, Crystal G. (Sierra7) (she/her/hers): - Users have tried to import forms that do not come from LEAF (Text Document file type is the current expected format). - Confirm that forms with multiple levels of If/Then logic properly import.
Note on F6: Kirscht, Crystal G. (Sierra7) (she/her/hers): - Users have tried to import forms that do not come from LEAF (Text Document file type is the current expected format). - Confirm that forms with multiple levels of If/Then logic properly import.
Note on A14: Kirscht, Crystal G. (Sierra7) (she/her/hers): - If trying to select prefill data from a file, need to ensure file exists in file manager and is properly set using if/then logic. - If prefilling a question with an OrgChart group based on if/then logic, the group needs to be established in site first before it can be incorporated into the If/Then logic.
Note on F14: Kirscht, Crystal G. (Sierra7) (she/her/hers): - Users forget that after the internal use form is created they need to associate the form to the expected step in the workflow. - Try to associate the same internal form to multiple steps in the workflow – data will be overwritten causing confusion – notes provided would be logged in the comments bar, but when running the report it will take the values from the last entry before completion.
Note on A21: Kirscht, Crystal G. (Sierra7) (she/her/hers): Pre-fill condition works for the following Input Format Types: • Single Line Text • Multi-line Text • Radio (single select, multiple options) • Checkboxes (multiple checkboxes) • Multi-select dropdown • Dropdown (single select, multiple options) • OrgChart Group • OrgChart Employee • OrgChart Position

## Submit A Request
Scenario | Tested | Assignee | Scenario | Tested | Assignee | Scenario | Tested | Assignee | Scenario | Tested | Assignee | Scenario | Tested | Assignee
Verify New Request Link is Functional |  |  | Request With Available Form Can be Copied | In Progress | Crystal | Request with Hidden Form Can Be Copied |  |  | Cancel Button is Hidden after Submitting for Non-Admin Users |  |  | Previous Value Still Available to Request After Restoring Question
Click on New Request | Yes | Crystal | Verify that form status is Available | Yes | Crystal | Verify the Form status is Hidden | Yes | Crystal | Go to Home page | No | Select Tester | Go to Form Editor | Yes | Crystal
Verify New Request screen is displayed | Yes | Crystal | Go to Home page | Yes | Crystal | Go to Home page | Yes | Crystal | Click on "Test Negative Currency" Request | No | Select Tester | Click on Multiple Person Designated | Yes | Crystal
Available Form is Visible to New Request |  |  | Click on "Request to Edit, Copy, and Cancel" | Yes | Crystal | Click on "Request to Edit, Copy, and Cancel" | Yes | Crystal | Verify Cancel button is visible | No | Select Tester | Click on Restore Fields | Yes | Crystal
Go to Form Editor | Yes | Crystal | Click on Copy Request | Yes | Crystal | Click on Copy Request | Yes | Crystal | Click on Submit Request | No | Select Tester | For the Reviewer 2 field, click on Restore this Field | Yes | Crystal
Click on Simple Form | Yes | Crystal | Click on 'Save Changes' | Yes | Crystal | Click on 'Save Changes' | Yes | Crystal | Verify the Cancel button is not visible | No | Select Tester | Click ok in the pop up window | Yes | Crystal
Change Status: to Available | Yes | Crystal | Change value to 'New Text Available | Yes | Crystal | Change value to 'New Text Hidden ' | Yes | Crystal | Go to Home Page | No | Select Tester | Verify the Reviewer 2 field is no longer listed | Yes | Crystal
Click on Home | Yes | Crystal | Click on Next Question | Yes | Crystal | Click on Next Question | Yes | Crystal | Click on "Test Negative Currency" Request | No | Select Tester | Click on Form Browser | Yes | Crystal
Click on New Request | Yes | Crystal | Go to Home page | Yes | Crystal | Go to Home page | Yes | Crystal | Verify Cancel button is still not visible | No | Select Tester | Click on Multiple Person Designated | Yes | Crystal
Verify 'Simple Form' is now available to select | Yes | Crystal | Verify there are 2 requests with the name "Request to Edit, Copy, and Cancel" | Yes | Crystal | Verify there are 3 requests with the name "Request to Edit, Copy, and Cancel" | Yes | Crystal | Create New Request |  |  | Verify Reviewer 2 field is again visible | Yes | Crystal
Edit a New Request |  |  | Unpublished Form Not Visible to New Request |  |  | Cancel Requests |  |  | Click on New Request | Yes | Crystal | Go to Home Page | Yes | Crystal
Click on New Request | Yes | Crystal | Go to Form Editor | Yes | Crystal | For each request with title "Request to Edit, Copy, and Cancel": | Yes | Crystal | Populate fields in Step 1 - General Information. Title request "Request to Create" | Yes | Crystal | Click on 'Request to Create' | Yes | Crystal
Select any service and put "Request to Edit, Copy, and Cancel" as the title | Yes | Crystal | Click on Simple Form | Yes | Crystal | Click on Cancel Request | Yes | Crystal | Check"Multiple Person Designated" in Step 2 - Select type of Request | Yes | Crystal | Verify Reviewer 2 is visible and populated with Dorian Balistreri | Yes | Crystal
Choose Simple Form under Step 2 | Yes | Crystal | Change Status: to Unpublished | Yes | Crystal | Click Yes on the popup | Yes | Crystal | Click on "Click Here to Proceed" | Yes | Crystal | Previous Value Still Available to Request After Restoring Question
Click on Select Here to Proceed | Yes | Crystal | Click on Home | Yes | Crystal | Verify screen saying request has been cancelled is displayed | Yes | Crystal | Fill in value for Reviewer 1 with userName:VTRSHHZOFIA | Yes | Crystal | Go to Form Editor | Yes | Crystal
Put 12345 in the 'single line text' field | Yes | Crystal | Click on New Request | Yes | Crystal | After all have been cancelled, verify the number of requests named "Request to Edit, Copy, and Cancel" is 0 | Yes | Crystal | Fill in value for Reviewer 2 with userName:VTRUXEJAMIE | Yes | Crystal | Click on Multiple Person Designated | Yes | Crystal
Click 'Next Question' | Yes | Crystal | Verify 'Simple Form' is not available to select | Yes | Crystal |  |  |  | Verify the selected name for Reviewer 1 is 'Bauch, Adam Koelpin' | Yes | Crystal | Click on Restore Fields | Yes | Crystal
Verify the value under 'single line text' is '12345' | Yes | Crystal | Request with Unpublished Form Cannot Be Copied |  |  | Negative Currency Allowed in New Request |  |  | Verify the selected name for Reviewer 2 is 'Balistreri, Dorian Dickens' | Yes | Crystal | Verify Field Name is Reviewer 2 | Yes | Crystal
Click on 'Edit this form' | Yes | Crystal | Verify the Form status is Unpublished? | Yes | Crystal | Go to New Request | Yes | Crystal | On the last page verify the reviewers information is correct and click Submit Request | Yes | Crystal | Click on Restore this Field | Yes | Crystal
Change the value to 'New Text' and click 'Next Question' | Yes | Crystal | Go to Home page | Yes | Crystal | Select any service and put Test Negative Currency as the title | Yes | Crystal | Verify request has been submitted | Yes | Crystal | Click on OK | Yes | Crystal
Verify the value now displays 'New Text' | Yes | Crystal | Click on "Request to Edit, Copy, and Cancel" | Yes | Crystal | Choose 'Input Formats' under Step 2 | Yes | Crystal | Archived Question Not Visible to New Request |  |  | Click on Form Browser | Yes | Crystal
Cancel Button is Visible after Submitting for Admin Users |  |  | Click on Copy Request | Yes | Crystal | Click Proceed to Next Question | Yes | Crystal | Go to Form Editor | Yes | Crystal | Click on Form | Yes | Crystal
Go to Home page | No | Select Tester | Click on 'Save Changes' | Yes | Crystal | Put a negative number in the currency box | Yes | Crystal | Click on Multiple Person Designated | Yes | Crystal | Verify Reviewer 2 question is visible | Yes | Crystal
Click on "Request to Edit, Copy, and Cancel" | No | Select Tester | Verify the message "Request could not be copied:" is displayed | Yes | Crystal | Click on Save Change | Yes | Crystal | In the Reviewer 2 question click on the Edit button | Yes | Crystal | Go to Home Page | Yes | Crystal
Verify Cancel button is visible | No | Select Tester | Hidden Form is Not Visible to New Request |  |  | Verify the negative number is displayed under the currency field | Yes | Crystal | Click on Archive and click Save | Yes | Crystal | Click on previously created request | Yes | Crystal
Click on Submit Request | No | Select Tester | Go to Form Editor | Yes | Crystal | Click on Show Single Page | Yes | Crystal | Verify Reviewer2 question is no longer visible | Yes | Crystal | Verify Reviewer 2 is visible | Yes | Crystal
Verify the Cancel button is still visible | No | Select Tester | Click on Simple Form | Yes | Crystal | Verify the negative number is displayed under the currency field | Yes | Crystal | Go to Home Page | Yes | Crystal | Verify Reviewer 2 contains Dorian Balistreri | Yes | Crystal
Go to Home Page | No | Select Tester | Change Status: to Hidden | Yes | Crystal | Negative Currency Allowed When Editing Request |  |  | Click on Request to Create | Yes | Crystal
Click on "Request to Edit, Copy, and Cancel" | No | Select Tester | Click on Home | Yes | Crystal | Go to Home Page | Yes | Crystal | Verify Reviewer 2 is no longer visible | Yes | Crystal
Verify Cancel button is visible | No | Select Tester | Click on New Request | Yes | Crystal | Choose 'Test Negative Currency' Request | Yes | Crystal | Select both reviewer fields | Yes | Crystal
|  |  | Verify 'Simple Form' is not available to select | Yes | Crystal | Click on the notepad in section 1 | Yes | Crystal | Click Generate Report | Yes | Crystal
[6 empty] | Change the currency input to another negative number | Yes | Crystal | Verify Reviewer 2 is populated with Dorian Balisteri | Yes | Crystal
[6 empty] | Click on Save Changes | Yes | Crystal
[6 empty] | Verify no errors occur | Yes | Crystal
[6 empty] | Verify the new value is displayed under the currency heading | Yes | Crystal
Value Still Visible in Report After Archiving Question
Go to Report Builder | Yes | Crystal
Change filter to Title CONTAINS Create | Yes | Crystal
Click on Next Step | Yes | Crystal
Click on Multiple Person Designated | Yes | Crystal

## Workflow Editor
Scenario | Method to Test | Tested | Assignee | Scenario | Method to Test | Tested | Assignee | Scenario | Method to Test | Tested | Assignee | Scenario | Method to Test | Tested | Assignee | Scenario | Method to Test | Tested | Assignee
Click on Admin Panel | Select Method | No | Select Tester | Remove Workflow Action |  |  |  | Add Event from Action Icon |  |  |  | Rename workflow |  |  |  | Create a new workflow and delete it
Click on Workflow Editor | Select Method | No | Select Tester | Click on newly added action | Select Method | Yes | Nikesh | Click on the Action Icon | Automate | Yes | Margo | Create a new workflow | Select Method | Yes | Nikesh | Create a new workflow | Automate | Yes | Nikesh
Create a new workflow and add step |  |  |  | Click Remove Action | Select Method | Yes | Nikesh | locate Event from the list | Automate | Yes | Margo | Renames the workflow | Select Method | Yes | Nikesh | Validate that the workflow appears in the dropdown | Automate | Yes | Nikesh
Click on New Workflow | Automate | Yes | Nikesh | Click Yes in the Confirm Action Removal Window | Select Method | Yes | Nikesh | Add Event | Automate | Yes | Margo | Fills in the new workflow name | Select Method | Yes | Nikesh | Delete the workflow | Automate | Yes | Nikesh
Enter a title and click Save | Automate | Yes | Nikesh | Verify the action was removed | Select Method | No | Nikesh | Verify Event is added to Workflow | Automate | Yes | Margo | Validates that the renamed workflow is visible | Select Method | Yes | Nikesh | Validate that the workflow is removed from the dropdown | Automate | Yes | Nikesh
Click on New Step | Automate | Yes | Nikesh | Create New Workflow Action (New)* |  |  |  | Close Modal | Automate | Yes | Margo
Enter a title and click Save | Automate | Yes | Nikesh | Drag Cat5 cable between 2 remaining steps | Select Method | No | Nikesh | Email Reminder for Inactivity* |  |  |  | View workflow history
Add Existing Requirement to Step |  |  |  | New action window will be displayed | Select Method | No | Nikesh | Click on a step | Select Method | In Progress | Nikesh | Create a new workflow | Automate | Yes | Nikesh
Click on Step and click Add Requirement | Automate | Yes | Nikesh | Click "Create a new Action Type" | Select Method | No | Nikesh | Click on Email Reminder | Select Method | In Progress | Nikesh | Click View History | Automate | Yes | Nikesh
Choose a requirement from the drop down | Automate | Yes | Nikesh | Use up/down to choose button order | Select Method | No | Nikesh | Select check box next to Enable Automated Emails | Select Method | In Progress | Nikesh | Verify the new workflow name appears in the history | Automate | Yes | Nikesh
Click Save | Automate | Yes | Nikesh | Choose Backwards or Forwards from the dropdown | Select Method | No | Nikesh | Select value from Type of Reminder drop down | Select Method | In Progress | Nikesh | Copy workflow
Add New Requirement to Step (must have User Group created) |  |  |  | Click on "List of Available Icons" | Select Method | No | Nikesh | Input additional values and click Save | Select Method | In Progress | Nikesh | Create and save a new workflow | Automate | Yes | Nikesh
Click on Step and click Add Requirement | Select Method | In Progress | Nikesh | Verify page with available icons loads | Select Method | No | Nikesh | Verify a Clock icon on the selected Step | Select Method | In Progress | Nikesh | Verify the original workflow visibility | Automate | Yes | Nikesh
Click on Create a New Requirement | Select Method | In Progress | Nikesh | Copy icon name and return to previous page | Select Method | No | Nikesh | Click on the step with the reminder | Select Method | In Progress | Nikesh | Drag and connect the start point to the end point | Automate | Yes | Nikesh
Enter a requirement label | Select Method | In Progress | Nikesh | Fill out fields including icon and click save | Select Method | No | Nikesh | Verify the correct email reminder information is shown | Select Method | In Progress | Nikesh | Click Copy Workflow and reload | Automate | Yes | Nikesh
Click Save | Select Method | In Progress | Nikesh | Reconnect steps | Select Method | No | Nikesh | Additional Actions (Need to be expanded) |  |  |  | Duplicate workflow and save | Automate | Yes | Nikesh
Select group from drop down menu | Select Method | In Progress | Nikesh | Verify new action is in drop down | Select Method | No | Nikesh | Edit an Action | Select Method | In Progress | Nikesh | Verify the copied workflow | Automate | Yes | Nikesh
Click Save | Select Method | In Progress | Nikesh | Select new action | Select Method | No | Nikesh | Change Action Icon | Select Method | In Progress | Nikesh
Group will be displayed under Requirements title | Select Method | In Progress | Nikesh | Click Save | Select Method | No | Nikesh | Create new Loop action type | Select Method | In Progress | Nikesh
Connect the Steps* |  |  |  | Verify new action is represented as a button | Select Method | No | Nikesh | Create new Loop workflow action | Select Method | In Progress | Nikesh
Drag Cat5 Cable from Requestor step to next step | Select Method | No | Nikesh | Create a New Event* |  |  |  | Test looped workflow action | Select Method | In Progress | Nikesh
Verify first step defaults to Submit | Select Method | No | Nikesh | Click on action | Automate | Yes | Margo | Verify Event Removed from Workflow Action |  |  |  | *Priority set by Harlie.
Create New Workflow Action (Existing) |  |  |  | Click Add Event | Automate | Yes | Margo | Click on the Requestor | Automate | Yes | Margo | To Note:
Drag Cat5 cable between 2 remaining steps | Select Method | No | Select Tester | Fill out Event Name and Description | Automate | Yes | Margo | Verify Event is not present | Automate | Yes | Margo | - On the last step of a workflow choose the "send to next approver" notification – this breaks the workflow
New action window will be displayed | Select Method | No | Select Tester | Click Save | Automate | Yes | Margo | Exit Modal | Automate | Yes | Margo
Choose an action from the drop down | Select Method | No | Select Tester | Verify Event has been added to the action | Automate | Yes | Margo | Verify Duplicate Event Name & Description are not Allowed' |  |  |  | - Same action cannot be used FROM the same step to multiple different steps – system will automatically remove the existing link; users sometimes do not notice and then wonder why their workflow is not fully completed.
Click Save | Select Method | No | Select Tester | Remove Event* |  |  |  | Click Edit Events | Automate | Yes | Margo
Confirm a new action of the selected type was added | Select Method | No | Select Tester | Click Edit Event | Automate | Yes | Margo | Enter non-unique Data | Automate | Yes | Margo
Create a Read Only Workflow Step* |  |  |  | Locate the Event | Automate | Yes | Margo | Modal popup | Automate | Yes | Margo
Add a step to the workflow but don't connect it to any other step | Select Method | Yes | Nikesh | Click Remove Action | Automate | Yes | Margo | close modal | Automate | Yes | Margo
Add a requirement to the step | Select Method | Yes | Nikesh | Click Yes | Automate | Yes | Margo | Exit Modal | Automate | Yes | Margo
Add Event from Side Navigation |  |  |  | Verify event was removed in List | Automate | Yes | Margo | View Email Template Editor | Automate | Yes | Select Tester
Click Edit Events | Automate | Yes | Margo | Edit Event |  |  |  | Edit Email Template Editor | Automate | Yes | Select Tester
Click Create a new Event | Automate | Yes | Margo | Click on Edit Event | Automate | Yes | Margo | Restore Orginal Email | Automate | Yes | Select Tester
Enter required Data | Automate | Yes | Margo | Locate the Event | Automate | Yes | Margo
Verify Event is added to the List | Automate | Yes | Margo | Click Edit | Automate | Yes | Margo
Close Modal | Automate | Yes | Margo | Update Fields | Automate | Yes | Margo
Remove Event |  |  |  | Click Save | Automate | Yes | Margo
Click Edit Events | Automate | Yes | Margo
Click Delete | Automate | Yes | Margo
Confirm you are deleting the form | Automate | Yes | Margo
Verify Event is deleted from the List | Automate | Yes | Margo
Close Modal | Automate | Yes | Margo
Note on K13: VHAISHKirscC: Reminders can't be set in hours or 0.5 days
Note on A30: VHAISHKirscC: Per Harlie, if a read only group is associated to a single workflow, but the site contains MULTIPLE forms and workflows, it is not an all-access permission. Read Only steps need to be added to each workflow in the site for full data access. this is used primarily for users who need to run reports but do not need to be part of a workflow. Should this be tested in another section?

## Report Builder
Scenario | Tested | Assignee | Scenario | Tested | Assignee | Scenario | Tested | Assignee
Column order is maintained after modifying the search filter |  |  | Report Allows Negative Currency - test for 4665 |  |  | Additional Tests Needed
Go to Report (what report is this? What was used to get this?) | Yes | Nikesh | Go to Report Builder | In Progress | Crystal | Filter using dropdowns | No | Select Tester
Verify Sort By Numeric is visible (What does this verify, I don't see it on the page) | Yes | Nikesh | Change query to Type IS Input Formats | In Progress | Crystal | Filter using checkboxes | No | Select Tester
Verify 4th column is numeric | Yes | Nikesh | Click on Next Step | In Progress | Crystal | View report generated | No | Select Tester
Click on Modify Search | Yes | Nikesh | Click on Input Formats | In Progress | Crystal | Modify search | No | Select Tester
Change search value to 8000 | Yes | Nikesh | Check the box next to 'currency' | In Progress | Crystal | Edit Labels | No | Select Tester
Click on Next Step | Yes | Nikesh | Click on 'Generate Report' | In Progress | Crystal | Share Report | No | Select Tester
Click on Generate Report | Yes | Nikesh | Click in an empty cell under 'currency' | In Progress | Crystal
Verify 4th column is still numeric | Yes | Nikesh | In the window enter a negative number in the currency field | In Progress | Crystal
Redirect to search filter and Generate Report with Approval History column |  |  | Click on Save Change | In Progress | Crystal
Step 1 | Yes | Nikesh | Verify the negative amount is displayed in the cell | In Progress | Crystal
Step 2 | Yes | Nikesh
List Additional steps as needed | Yes | Nikesh
Update and revert report title from pop-up window
Step 1 | Yes | Nikesh
Step 2 | Yes | Nikesh
List Additional steps as needed | Yes | Nikesh
Navigation to record page on UID link click
Step 1 | Yes | Nikesh
Step 2 | Yes | Nikesh
List Additional steps as needed | Yes | Nikesh
Update current status to Initiator to generate report with reports
Step 1 | Yes | Nikesh
Step 2 | Yes | Nikesh
List Additional steps as needed | Yes | Nikesh
Comment approval functionality and comment visibility on record page
Step 1 | Yes | Nikesh
Step 2 | Yes | Nikesh
List Additional steps as needed | Yes | Nikesh
Share Report button is visible on the UI
Step 1 | Yes | Nikesh
Step 2 | Yes | Nikesh
List Additional steps as needed | Yes | Nikesh
Report builder workflow and create row button functionality
Step 1 | Yes | Nikesh
Step 2 | Yes | Nikesh
List Additional steps as needed | Yes | Nikesh

## Nexus
Setup Wizard
Scenario | Method to Test | Tested | Assignee
Go to OC Admin | Select Method | In Progress | Margo
Go to Setup Wizard | Select Method | In Progress | Margo
Go to System Administrators | Select Method | In Progress | Margo
Go to Site Preferences | Select Method | In Progress | Margo
Go to Site Director | Select Method | In Progress | Margo
Add a new Director (select existing director) | Select Method | No | Select Tester
Add Employee as Network Director | Select Method | No | Select Tester
Go to Exectutive Leadership Team | Select Method | No | Select Tester
Create Group for ELT | Select Method | No | Select Tester
Add Service to ELT | Select Method | No | Select Tester
Change the Superviser of a Service | Select Method | No | Select Tester
Edit Service (Group) name | Select Method | No | Select Tester
Delete Service (Group) | Select Method | No | Select Tester
View Organizational Chart
Verify you able to view Organizational Chart | Automate | In Progress | Margo
Click on a tab to see more information | Automate | In Progress | Margo
Expand the information | Automate | In Progress | Margo
Verify you are able to see all details | Automate | In Progress | Margo
Edit Organizational Chart
Click Edit Org Chart | Select Method | No | Select Tester
Verify you have the ability to | Select Method | No | Select Tester
| Select Method | No | Select Tester
| Select Method | No | Select Tester
| Select Method | No | Select Tester
| Select Method | No | Select Tester
| Select Method | No | Select Tester
| Select Method | No | Select Tester
| Select Method | No | Select Tester
| Select Method | No | Select Tester
| Select Method | No | Select Tester
| Select Method | No
| Select Method | No

## Sitemap and Combined Inbox
Scenario | Method to Test | Tested | Assignee | Scenario | Method to Test | Tested | Assignee
Sitemap Editor* |  |  |  | Combined Index Editor*
Click on Admin Panel | Select Method | Yes | Nikesh | Click on Admin Panel | Select Method | No | Select Tester
Click on Sitemap Editor under Toolbox | Select Method | Yes | Nikesh | Click on Combined Inbox Editor under Toolbox | Select Method | No | Select Tester
Click on "+Add Site" | Select Method | Yes | Nikesh | Verify each configured inbox is displayed with default columns | Select Method | No | Select Tester
Type in Site Title and Site Description | Select Method | Yes | Nikesh | Remove a Column*
Paste the copied URL from the note into the Target Site Address field | Select Method | Yes | Nikesh | Click on the x next to one of the column name buttons to remove | Select Method | No | Select Tester
Click on Site Color | Select Method | Yes | Nikesh | Verify column name has been removed | Select Method | No | Select Tester
Choose a color for the Sitemap Editor Tile | Select Method | Yes | Nikesh | Add a New Column*
Click on Font Color | Select Method | Yes | Nikesh | Click on "Click to Search" to the right of the column names | Select Method | No | Select Tester
Choose a color for font displayed on the Sitemap Editor Tile | Select Method | Yes | Nikesh | Select a column name from the pop up list | Select Method | No | Select Tester
Choose an icon to be displayed on the Sitemap Editor Time | Select Method | Yes | Nikesh | Confirm the column is added to the list of column names | Select Method | No | Select Tester
Click Save Change | Select Method | Yes | Nikesh | Add Columns from a Form*
Verify the new tile has all the desired feature selected | Select Method | Yes | Nikesh | Click on Select a Form | Select Method | No | Select Tester
|  |  |  | Choose a form from the dropdown | Select Method | No | Select Tester
|  |  |  | Click on "Click to Search" to the right of the column names | Select Method | No | Select Tester
|  |  |  | Verify the columns from the selected form are listed | Select Method | No | Select Tester
Change Inbox Order*
|  |  |  | Reorder the display of inboxes by dragging and dropping the desired Inbox Title | Select Method | No | Select Tester
|  |  |  | Verify the order of the Inboxes matches the order under Edit Columns | Select Method | No | Select Tester
*Priority designated by Harlie
Note on A2: Kirscht, Crystal G. (Sierra7) (she/her/hers): Before proceding be sure to have the URL of another LEAF site copied or available to copy
Note on F2: Kirscht, Crystal G. (Sierra7) (she/her/hers): Multiple sites must be set up as described above and Combined Inbox must be configured Issues: - Expecting the Combined Inbox to be visible but sitemap editor is not yet established. - This requires the combined inbox link to be added to the home page or provided to the user for access.
Note on F13: Kirscht, Crystal G. (Sierra7) (she/her/hers): You can only select fields from one Form in each inbox. Changing the type of form resets the inbox selections

## User Access Group
Scenario | Status | Assignee | Scenario | Status | Assignee
Create group and add an employee |  |  | System admin search
Create a New Group | In Review | Nikesh | Navigate to System Admins Page | In Review | Nikesh
Verify Group Creation | In Review | Nikesh | Search for System Admin | In Review | Nikesh
Open the New Group and Search and Add an Employee | In Review | Nikesh | Verify System Admin Exists | In Review | Nikesh
Verify Employee in Group | In Review | Nikesh | Verify Other Admin Not Found | In Review | Nikesh
Import a group from another leaf site and delete it |  |  | View user group history
Open Import Group Dialog | In Review | Nikesh
Search and Select Group to Import | In Review | Nikesh | Open a specific group | In Review | Nikesh
Import the Group | In Review | Nikesh | Click the "View History" button | In Review | Nikesh
Verify Group Import | In Review | Nikesh | Verify the group name in the history | In Review | Nikesh
Open the Imported Group | In Review | Nikesh | Close the group history modal | In Review | Nikesh
Delete the Group | In Review | Nikesh
Verify Deletion | In Review | Nikesh

## Additional Features
Scenario | Method to Test | Tested | Assignee | Scenario | Method to Test | Tested | Assignee | Scenario | Method to Test | Tested | Assignee
User Access Groups* |  |  |  | New Account Updater |  |  |  | Miscellaneous
Click on Admin Panel | Select Method | Yes | Nikesh | Click on New Account Updater | Select Method | Yes | Margo | View Request History | Select Method | No | Select Tester
Click on User Access Groups | Select Method | Yes | Nikesh | Search for Old Account | Select Method | Yes | Margo | Modify and save site settings | Select Method | No | Select Tester
Add a New Group* |  |  |  | Search for New Account | Select Method | Yes | Margo | Set a Bookmark | Select Method | No | Select Tester
Click on +Create group | Select Method | Yes | Nikesh | Preview Changes | Select Method | Yes | Margo | Confirm bookmark is set | Select Method | No | Select Tester
Add a title and click Save | Select Method | Yes | Nikesh | Update New Account | Select Method | Yes | Margo | View Timeline (need to set from to at least 2 years ago) | Select Method | No | Select Tester
New group should appear in User Groups section | Select Method | Yes | Nikesh | Check the new account has the updated values | Select Method | Yes | Margo | View Add Site options (need a URL to add site) | Select Method | No | Select Tester
Add Users* |  |  |  | Viewing a LEAF Inbox*
Click on newly created group | Select Method | Yes | Nikesh | Click on Inbox (may say Combined Inbox) | Select Method | No | Select Tester | *Priority designated by Harlie
Search for user to add by last name, first name | Select Method | Yes | Nikesh | Verify the Inbox is displayed | Select Method | No | Select Tester
Click on user 's name in list of results | Select Method | Yes | Nikesh | Click on Toggle sections to expand/collapse rows | Select Method | No | Select Tester
Click Save | Select Method | Yes | Nikesh | Click on Organize by Roles to organize by role/form | Select Method | No | Select Tester
Verify the selected user has been added | Select Method | Yes | Nikesh | Click on View as Admin to view all items in inbox | Select Method | No | Select Tester
Remove Users |  |  |  | Click on View as non-Admin to view only items for your assigned roles | Select Method | No | Select Tester
Click on group | Select Method | Yes | Nikesh | Click on View Original Inbox | Select Method | No | Select Tester
Click on Remove button next to user to be removed | Select Method | Yes | Nikesh | Verify the original layout of the inbox is displayed | Select Method | No | Select Tester
Click on Save | Select Method | Yes | Nikesh
Verify that user has been removed | Select Method | Yes | Nikesh
View Group History
Click on group | Select Method | Yes | Nikesh
Click on View History | Select Method | Yes | Nikesh
Verify Group History window is displayed | Select Method | Yes | Nikesh
Delete Group
Click on group | Select Method | Yes | Nikesh
Click on Delete Group | Select Method | Yes | Nikesh
Click Yes on the question pop up | Select Method | Yes | Nikesh
Verify Group has been deleted | Select Method | Yes | Nikesh
Mass Action
Perform a Mass action on a single record | Select Method | No | Select Tester
Perform a Mass action on all recrods | Select Method | No | Select Tester
Send an email reminder | Select Method | No | Select Tester
Note on A2: Kirscht, Crystal G. (Sierra7) (she/her/hers): users cannot use an email distribution list within a user group.
Note on F12: Kirscht, Crystal G. (Sierra7) (she/her/hers): If the user has only 1 role and it is associated to only 1 form then the only change in their view they would see is the title change on the header bar.
Note on F14: Kirscht, Crystal G. (Sierra7) (she/her/hers): Only system admins should be able to see all actions in the inbox.

## PRs Needing Tests
PR Number | Description | Reason Can't Be Tested
4667 | Add Cancel Button Template Logic | Unable to change user admin status
4669 | Required Validator Reset Logic Correction | Requires a complicated form and only happens in rare cases